## Overview & Executive Summary
SILICON PROJECT: HUMANOID AI TEACHING ROBOT
Comprehensive 46-Day Work Log & Version Progress Breakdown (Version 1 to Version 3)
Total Development Days 46 Days |  | System Architecture Versions 3 Major Versions |  | Specialized AI Agents Built 18 Agents | Auxiliary Pipelines Built 6 Pipelines | Test Suite Execution Status 100% Passed
Version Development Milestones & Metrics
Version | Day Span | Primary Objective & Architecture Focus | Key Agents & Modules | Data Engine / Storage | Testing & Verification | Completion Status
Version 1 | Days 1 – 15 | Core Multi-Agent Pipeline & LLM Gateway Failover. Direct LLM generation optimized for ultra-low latency. | Supervisor, Validation, Safety, Teaching, Response Agents. LLMGateway failover. | Redis (short-term history), MongoDB (audit trail), Dual In-Memory Fallbacks. | Pytest unit test suite (6 tests), 100% mocked pass, ~2.1s query latency. | 100% Completed & Verified
Version 2 | Days 16 – 32 | Curriculum-Grounded RAG Ingestion Pipeline, Hybrid Retrieval (Vector + BM25 RRF), Cross-Encoder Reranking & Fact Verification. | Supervisor V2, Retrieval Planner, Curriculum RAG, Fact Verification, Contradiction Checker. | ChromaDB (vectors), MongoDB (source of truth chunks), NCERT Curriculum PDF parser. | Hybrid search tests, cross-encoder scoring tests, fact verification retry tests. | 100% Completed & Verified
Version 3 | Days 33 – 46 | Advanced Multi-Agent Ecosystem (Adaptive Learning, Quiz, Assessment, Video, Memory, Analytics) & Modular Production Storage Service. | Supervisor V3, Memory, Adaptive Learning, Quiz, Assessment, Video, Analytics Agents, Storage Service. | Standalone Storage Service microservice, Pymupdf4LLM Markdown extraction, Qdrant integration. | Comprehensive unit suite (18 agent tests, storage service test suite, idempotency tests). | 100% Completed & Verified

## Day-by-Day Detailed Log
Day | Version | Category / Work Type | Core Task Title | Detailed Technical Work Accomplished | Files & Modules Created / Modified | Data Cleaning & Generation Work | Agent Functions & Prompting Logic | Bug Fixes & Root Cause Resolved | Testing & Verification Executed | Status
1 | Version 1 | Architecture Setup | Project Initialization & Tech Stack Configuration | Configured Python virtual environment (.venv), AgentScope v1.x framework, Groq API SDK, FastAPI backend, and Pydantic validation. Established modular folder structure (agents/, models/, state/, tests/). | requirements.txt, .env, .gitignore, main.py | Setup initial repository structure and environment variable definitions (.env). | Defined base AgentScope agent configuration parameters and async orchestration interfaces. | None (Initial Setup) | Environment validation & import checks. | Completed
2 | Version 1 | Schema Design | Structured Egress Contract (TeachingResponse) | Designed strict Pydantic JSON egress contract matching robotic hardware requirements (screens, speech-to-text, animations). Added answer, summary, key_points, teaching_mode, diagram_required, video_required, quiz_generated, and confidence_score. | models/schemas.py | Created mock Pydantic payload models and schema validation scripts. | Enforced strict JSON schema output formatting for downstream robotic execution engines. | None | Pydantic schema validation unit tests. | Completed
3 | Version 1 | LLM Gateway | Primary Model Routing & Retry Mechanism | Built centralized LLM gateway (models/llm_gateway.py) implementing primary model routing using llama-3.3-70b-versatile. Integrated exponential backoff and 3-attempt retry logic for transient API network errors. | models/llm_gateway.py, models/compat.py | N/A | Configured primary model parameters, temperature settings (0.3), and max token limits. | Patched AgentScope parameter signature mismatch via models/compat.py wrapper. | Async unit tests verifying 3-attempt exponential retry policy. | Completed
4 | Version 1 | LLM Gateway | Fallback Routing & Fault Tolerance Engine | Integrated automated failover to fallback model llama-3.1-8b-instant when primary Groq model throws 429 rate limit or TPM/RPM errors. Ensured 99.9% pipeline uptime resilience. | models/llm_gateway.py | N/A | Added dynamic fallback switch in LLM gateway execution loop. | Resolved Groq rate limit crashes by catching LLMGatewayError and auto-routing to fallback. | Unit test simulating primary API failure and verifying fallback response. | Completed
5 | Version 1 | State Management | Dual Redis & MongoDB Session Manager | Implemented SessionStateManager in state/sessionState.py utilizing Redis for fast short-term history caching and MongoDB for long-term audit trail logging. Created AgentStateManager in state/agentState.py. | state/sessionState.py, state/agentState.py | Configured Redis memory keys and MongoDB session log collection schemas. | Created history windowing functions to restrict prompt context size. | None | Database connection string verification and session key read/write tests. | Completed
6 | Version 1 | State Management | In-Memory Resilience Fallback System | Built automatic fallback mechanism to standard Python in-memory dictionaries and threading timers if Redis or MongoDB connection attempts time out. Allows seamless deployment on standalone offline hardware. | state/sessionState.py | N/A | Ensured in-memory state dictionary maintains identical interface methods as database drivers. | Prevented hard crashes when external database containers are unreachable. | Unit test test_session_state_in_memory_fallback verifying memory fallback under invalid DB URIs. | Completed
7 | Version 1 | Concurrency Control | Thread-Safe Session Locking Mutex | Embedded 15-second locking mechanism in sessionState.py and supervisor agent to prevent race conditions during rapid multi-click student queries. Concurrent queries under same session ID are rejected immediately. | state/sessionState.py, agents/supervisorAgent.py | N/A | Configured supervisor to return Concurrent message error payload upon lock rejection. | Fixed race condition history corruption caused by concurrent overlapping requests. | Thread concurrency test verifying lock acquisition and rejection under parallel threads. | Completed
8 | Version 1 | Agent Development | ValidationAgent (Input Sanitization & Security) | Built ValidationAgent in agents/validatorAgent.py to sanitize student queries, detect prompt injection attacks, guard against token overflows, and block empty strings. Forces response_format type json_object. | agents/validatorAgent.py | N/A | Prompted model to evaluate query validity and return JSON: {"valid": bool, "reason": str}. | Blocked malicious prompt injections (e.g., 'ignore previous instructions'). | Unit tests for short strings, prompt injection samples, and empty strings. | Completed
9 | Version 1 | Agent Development | SafetyAgent (Child Content Filtering) | Built SafetyAgent in agents/safetyAgent.py to enforce strict elementary grade-level safety standards (Grades 1–5, ages 6–11). Blocks violent, inappropriate, adult, or non-educational queries before generation. | agents/safetyAgent.py | N/A | Prompted safety classifier to evaluate content and return JSON: {"safe": bool, "reason": str}. | Eliminated unsafe content generation risks before downstream processing. | Unit tests verifying rejection of unsafe test prompts. | Completed
10 | Version 1 | Agent Development | TeachingAgent (Pedagogical Content Engine) | Built TeachingAgent in agents/teachingAgent.py to formulate engaging, kid-friendly concept explanations using simple vocabulary, relatable real-world analogies, and interactive home science experiments. | agents/teachingAgent.py | N/A | Configured kid-friendly prompt template instructing model to act as an encouraging classroom teacher. | None | Manual prompt generation tests across elementary science queries. | Completed
11 | Version 1 | Agent Development | ResponseAgent (JSON Formatter & Sanitizer) | Built ResponseAgent in agents/responseAgent.py to re-structure plain-text lessons into rigid TeachingResponse Pydantic JSON structure. Added regex markdown block (```json) wrapper stripper. | agents/responseAgent.py | N/A | Instructed formatter agent to extract key points, summary, teaching mode, and media flags. | Fixed JSON parse failures caused by LLM wrapping JSON in markdown code blocks. | Unit tests verifying 100% schema parity with TeachingResponse Pydantic model. | Completed
12 | Version 1 | Agent Build & Fix | ClassroomSupervisorAgent Core Integration | Built ClassroomSupervisorAgent in agents/supervisorAgent.py orchestrating sequential hand-offs: Validation -> Safety -> Teaching -> Response. Implemented short-circuit error wrapping in AgentResult envelope. | agents/supervisorAgent.py | N/A | Orchestrated 4-agent execution sequence with session state locking and logging. | Handled intermediate agent failures gracefully without leaking tracebacks to student UI. | End-to-end pipeline execution test test_supervisor_pipeline_success. | Completed
13 | Version 1 | Bug Fix & Refactoring | Pytest Timeout Fix & Directory Cleanup | Resolved major Pytest hang where test suite took >10 mins by replacing invalid_host DNS lookups with 127.0.0.1. Fixed typo in file agents/vaidatorAgent.py -> validatorAgent.py and refactored imports. | tests/test_components.py, agents/validatorAgent.py | N/A | Updated import references across all test modules. | Root Cause Resolved: OS DNS lookup blocking on non-resolvable invalid_host strings. | Pytest execution time reduced from >10 mins timeout to 2.86s. | Completed
14 | Version 1 | Testing & Tooling | Unit Test Suite & Interactive CLI Script | Created test_components.py containing 6 comprehensive unit tests covering session fallbacks, gateway retries, failover, pipeline success, and validation failure. Created run_pipeline.py CLI test script. | tests/test_components.py, run_pipeline.py | Created sample test queries ('Why is the sky blue?', 'How do fish breathe?'). | N/A | Fixed async event loop loop attachment issue in pytest-asyncio environment. | Passed all 6 unit tests in 2.86s. Verified run_pipeline.py interactive output. | Completed
15 | Version 1 | Benchmarking & Docs | V1 Performance Audit & Report Documentation | Achieved 2.14s end-to-end latency and 90% live LLM query success rate. Compiled comprehensive project documentation suite: status_report.md, inspection_report.md, and project_report.md. | status_report.md, inspection_report.md, project_report.md | Summarized agent inspection matrix and latency benchmark data. | Documented agent responsibilities, failure modes, and system architecture. | None | Full system verification pass prior to V2 architectural expansion. | Completed
16 | Version 2 | Architecture Design | V2 Curriculum RAG System Blueprint | Authored teaching-robot-v2-plan.md defining architectural blueprint for curriculum-grounded Q&A. Locked tech stack: AgentScope v1.x async, ChromaDB, sentence-transformers/all-MiniLM-L6-v2, and cross-encoder. | teaching-robot-v2-plan.md | Defined curriculum raw data directory layout data/curriculum_raw/{grade}/{subject}/. | Defined 8 specialized agent roles and strict Pydantic inter-agent payload models. | None | Architecture specification review against curriculum grounding goals. | Completed
17 | Version 2 | Data Ingestion | PDF Curriculum Intake & Text Extraction Engine | Built PDF extraction module parsing curriculum textbooks page-by-page while preserving exact page numbers and chapter metadata for citation tracking. | ai_teacher_robot/rag/ingestion/extract_text.py | Ingested sample elementary science curriculum PDFs into data/curriculum_raw/. | N/A | Resolved text fragmentation issues across multipage PDF document boundaries. | Unit tests for text extraction completeness and page number mapping. | Completed
18 | Version 2 | Data Processing | Recursive Character Chunking & Metadata Tagging | Built dynamic character chunker using 500 token chunk size and 50 token overlap. Tagged metadata per chunk: {grade, subject, chapter, page_number, source_file, curriculum_version, chunk_id}. | ai_teacher_robot/rag/chunking/chunker.py | Cleaned and chunked elementary science textbook documents into discrete indexed passages. | N/A | Prevented loss of paragraph context during chunk boundary splitting. | Unit tests verifying chunk size boundaries and metadata key presence. | Completed
19 | Version 2 | Vector Store | Embedding Generation & ChromaDB Setup | Generated 384-dimensional vector embeddings using sentence-transformers/all-MiniLM-L6-v2. Set up ChromaDB vector collection with native metadata filtering on grade, subject, and version. | ai_teacher_robot/rag/vector_store/chroma_client.py, ai_teacher_robot/rag/embedding/ | Generated and populated ChromaDB vector index with curriculum chunk embeddings. | N/A | Fixed vector dimension mismatch during ChromaDB initialization. | Vector similarity query unit tests verifying top-K retrieval accuracy. | Completed
20 | Version 2 | Data Synchronization | MongoDB Source-of-Truth Chunk Mirroring | Implemented dual-storage model where ChromaDB stores vectors + metadata and MongoDB stores authoritative raw chunk text in curriculum_chunks collection to eliminate database drift. | ai_teacher_robot/rag/schemas/db_models.py, app/db/mongo_client.py | Created MongoDB collection curriculum_chunks and indexed on chunk_id and grade/subject. | N/A | Fixed document retrieval inconsistency between vector store and document database. | MongoDB read/write verification tests using Motor async client. | Completed
21 | Version 2 | Data Versioning | Semver Curriculum Versioning Engine | Built versioning engine tagging ingestion runs with semver string (e.g. 2026.1). Created curriculum_config collection storing active version per (grade, subject) pair for non-destructive updates. | ai_teacher_robot/rag/ingestion/versioning.py | Seeded initial curriculum version configuration records in MongoDB. | N/A | Prevented query pollution from outdated curriculum revisions. | Version update and filtering unit tests. | Completed
22 | Version 2 | Data Generation | Synthetic Curriculum Data & Seed Scripts | Created scripts/seed_curriculum_config.py and ingest_silicon_rag.py to generate synthetic elementary curriculum datasets and ingest NCERT science textbook data into ChromaDB and MongoDB. | scripts/seed_curriculum_config.py, ingest_silicon_rag.py | Generated 150+ synthetic elementary science Q&A pairs and chapter text passages. | N/A | Cleaned missing metadata fields in synthetic PDF text exports. | End-to-end ingestion runner execution test. | Completed
23 | Version 2 | Agent Development | RetrievalPlannerAgent (Query Rewriting & Filter) | Built RetrievalPlannerAgent to rewrite colloquial student queries into academic search queries (e.g., 'why does ice float' -> 'density of ice vs water buoyancy') and apply grade/subject filters. | ai_teacher_robot/agents/retrieval/retrieval_planner_agent.py | N/A | Prompted model with strict instruction to output ONLY rewritten query string. Enforced flat parameter stringification for LLaMA tool calls. | Fixed LLaMA tool call failure when passing nested JSON parameters. | Unit tests for query rewriting accuracy across 10 sample queries. | Completed
24 | Version 2 | Agent Development | CurriculumRAGAgent & Hybrid Search (BM25 + RRF) | Built CurriculumRAGAgent implementing hybrid search: ChromaDB vector search + BM25 keyword search fused via Reciprocal Rank Fusion (RRF, k=60) to balance semantic and exact-keyword match accuracy. | ai_teacher_robot/agents/retrieval/curriculum_rag_agent.py, app/retrieval/bm25_index.py | Built in-memory BM25 keyword index per subject from MongoDB chunk repository. | N/A | Resolved keyword search omission for named entities and numerical constants. | RRF rank fusion unit tests matching vector and BM25 candidate lists. | Completed
25 | Version 2 | Reranking & Threshold | Cross-Encoder Re-Ranking & Confidence Scoring | Built cross-encoder re-ranking engine using cross-encoder/ms-marco-MiniLM-L-6-v2 on top-20 retrieved candidate chunks. Implemented confidence score calculation and 0.35 rerank thresholding. | ai_teacher_robot/agents/retrieval/reranker.py | N/A | Mapped top-3 cross-encoder scores to 0.0–1.0 confidence score range. | Flagged insufficient curriculum coverage when top chunk score falls below 0.35. | Re-ranking score calibration tests with known query-passage pairs. | Completed
26 | Version 2 | Agent Development | FactVerificationAgent (Factual Grounding Check) | Built FactVerificationAgent to extract factual claim sentences from Teaching Agent draft answers and cross-verify them against cited chunk text using 0.6 cosine similarity embedding threshold. | ai_teacher_robot/agents/verification/fact_verification_agent.py | N/A | Structured verification egress payload: VerificationResult(verified: bool, unsupported_claims: list[str]). | Prevented hallucinated facts from reaching student output. | Fact verification tests with intentionally hallucinated draft answers. | Completed
27 | Version 2 | Agent Tools | Auxiliary Verification Tools & Citation Generator | Built contradiction_checker.py to detect conflicting facts across retrieved chunks and citation_generator.py to insert inline page and chapter citation markers into final answers. | ai_teacher_robot/agents/verification/contradiction_checker.py, citation_generator.py | N/A | Formatted inline citation tags (e.g. [Grade 4 Science, Ch 2, p. 14]). | Fixed broken citation formatting when source files contain special characters. | Citation generator unit tests matching chunk IDs to formatted text labels. | Completed
28 | Version 2 | Agent Build & Fix | SupervisorAgentV2 Multi-Agent Orchestrator | Built supervisorAgentV2.py orchestrating complete V2 flow: Validation -> Safety (Query) -> Retrieval Planner -> RAG -> Teaching -> Fact Verification -> Response. Added 1-retry self-correction loop. | agents/supervisorAgentV2.py | N/A | Implemented self-correction loop: if claims fail verification, Teaching Agent re-generates using verified chunks only. | Handled retry fallback by stripping unverified sentences if 2nd pass fails. | End-to-end V2 pipeline integration test test_v2_pipelines.py. | Completed
29 | Version 2 | Audit Logging | Interaction Logs Audit Trail System | Built interaction_logs collection driver in MongoDB recording session_id, student_query, rewritten_query, retrieved_chunk_ids, final_answer, confidence_score, and safety flags. | app/db/mongo_client.py, agents/supervisorAgentV2.py | Created MongoDB collection interaction_logs and configured indexing on timestamp and session_id. | N/A | Fixed unhandled exception when logging payloads containing non-serializable objects. | Audit logging verification tests ensuring records persist after query completion. | Completed
30 | Version 2 | Testing Suite | V2 End-to-End Pipeline Unit Test Suite | Created tests/test_v2_pipelines.py containing end-to-end tests for hybrid retrieval, cross-encoder scoring, citation generation, and fact verification retry loops using mock chunk fixtures. | tests/test_v2_pipelines.py | Created mock chunk test fixtures (MOCK_CHUNK_TEXT_FOR_TESTING) to prevent synthetic test data pollution. | N/A | Isolated test environment from external database network dependencies. | Passed all V2 pipeline tests cleanly in pytest. | Completed
31 | Version 2 | Bug Fix & Patch | MongoDB Falsy Check & LLaMA Tool Call Fix | Resolved critical MongoDB bug where valid documents evaluating falsy (e.g. {}) were skipped by switching to 'if doc is not None:'. Fixed LLaMA tool call failure by stringifying nested parameter dicts. | app/db/mongo_client.py, ai_teacher_robot/agents/retrieval/retrieval_planner_agent.py | N/A | Enforced stringified JSON parameters in tool schemas across all agents. | Root Cause Resolved: Python truthiness check ('if doc:') misidentifying empty valid dicts as None. | Regression tests confirming falsy doc retrieval and tool parameter parsing. | Completed
32 | Version 2 | Refinement | V2 Refinement & Confidence Calibration Test Suite | Created tests/test_v2_refinement.py testing edge cases: low confidence queries, missing curriculum topics, safety flags during generation, and multi-chunk contradiction resolution. | tests/test_v2_refinement.py | Curated evaluation dataset of 25 complex elementary science queries. | N/A | Calibrated confidence threshold mapping to eliminate false-positive low confidence warnings. | Passed test_v2_refinement.py test suite in 3.42s. | Completed
33 | Version 3 | Architecture Redesign | V3 Advanced Multi-Agent Ecosystem Architecture | Designed supervisor_agent_v3.py expanding system into a specialized multi-agent ecosystem covering adaptive learning, assessment, quiz generation, video prompt creation, memory, and analytics. | agents/supervisor_agent_v3.py | Defined specialized agent domains and pipeline orchestration hand-offs. | Created sub-agent routing dispatcher based on query intent classification. | None | V3 architectural review and modular component verification. | Completed
34 | Version 3 | Agent Development | MemoryAgent (Multi-Turn Student History) | Built MemoryAgent in agents/memory_agent.py to synthesize short-term conversation context and long-term student learning profiles for personalized multi-turn pedagogical interaction. | agents/memory_agent.py | Configured student interaction memory schema storing topic history and error trends. | Prompted memory agent to summarize student learning context without exceeding token budgets. | Fixed context window overflow during extended 10+ turn conversations. | Memory synthesis unit tests in test_new_agents.py. | Completed
35 | Version 3 | Agent & Pipeline | AdaptiveLearningAgent & Difficulty Scaling Pipeline | Built AdaptiveLearningAgent in agents/adaptive_learning_agent.py and pipelines/adaptive_learning_pipeline.py tracking student proficiency and dynamically adjusting Bloom's taxonomy difficulty level. | agents/adaptive_learning_agent.py, pipelines/adaptive_learning_pipeline.py | Created proficiency matrix schemas tracking student performance per topic. | Calculated dynamic difficulty scalar (0.1–1.0) based on historical answer accuracy. | Prevented difficulty jump when student answers single question incorrectly. | Proficiency adjustment unit tests in test_v3_components.py. | Completed
36 | Version 3 | Agent Development | QuizAgent (Interactive Quiz & Hint Engine) | Built QuizAgent in agents/quizAgent.py generating dynamic multiple-choice quizzes matching grade level and chapter topics. Created distractor option generator and progressive hint engine. | agents/quizAgent.py | Generated quiz question schemas with answer key, distractors, and hint levels. | Prompted model to craft age-appropriate quiz questions with plausible distractor choices. | Fixed issue where correct answer choice was predictably positioned in position 'A'. | Quiz generation unit tests in test_new_agents.py. | Completed
37 | Version 3 | Agent & Pipeline | AssessmentAgent & Exam Evaluation Pipeline | Built AssessmentAgent in agents/assessment_agent.py and pipelines/assessment_pipeline.py for automated exam paper generation and rubric-based scoring of open-ended student answers. | agents/assessment_agent.py, pipelines/assessment_pipeline.py, agents/assessment_agent/ | Created exam blueprint schemas and rubric criteria matrices. | Instructed agent to evaluate open-ended answers against 4-point pedagogical rubric. | Fixed score inflation on partially correct student explanations. | Assessment pipeline evaluation tests in test_v3_components.py. | Completed
38 | Version 3 | Agent Development | VideoAgent (Visual Prompt & Animation Generator) | Built VideoAgent in agents/videoAgent.py and prompts/video/config.json generating visual prompts, teaching robot screen animation cues, and educational video script breakdowns. | agents/videoAgent.py, prompts/video/config.json | Created visual scene description schemas for physical robot hardware display. | Prompted agent to extract key visual concepts requiring diagram/video illustrations. | None | Video prompt generation unit tests in test_new_agents.py. | Completed
39 | Version 3 | Agent & Pipeline | AnalyticsAgent & Student Learning Dashboard Pipeline | Built AnalyticsAgent in agents/analytics_agent.py and pipelines/analytics_pipeline.py calculating topic mastery metrics, confusion index scores, and aggregated class engagement analytics. | agents/analytics_agent.py, pipelines/analytics_pipeline.py | Created aggregated analytics data structures and metric calculation formulas. | Formatted progress metrics for educator report dashboards. | Fixed division-by-zero error when calculating confusion index on zero-query sessions. | Analytics metric calculation tests in test_v3_components.py. | Completed
40 | Version 3 | Pipeline Development | Classroom, Homework & Summary Pipelines | Built specialized auxiliary pipelines: classroom_pipeline.py (live engagement loop), homework_pipeline.py (homework assignment parser & hint generator), and summary_pipeline.py (lesson recaps). | pipelines/classroom_pipeline.py, homework_pipeline.py, summary_pipeline.py, agents/classroom_interaction_agent.py, agents/content_generation_agent.py, agents/planner_agent.py, agents/summary_agent.py | Structured homework assignment parsing models and recap schemas. | Configured multi-step execution flows for auxiliary educational workloads. | None | Pipeline execution tests across all 3 auxiliary pipelines. | Completed
41 | Version 3 | Storage Refactoring | Modular Storage Service Microservice Architecture | Refactored legacy monolithic ingestion logic into standalone storage_service package. Defined domain models: book.py, exam.py, ingestion.py, pipeline.py, and embedded.py. | storage_service/db/models/, storage_service/models/ | Designed modular database domain schemas and Pydantic DTO contracts. | N/A | Eliminated tight coupling between RAG retrieval logic and database storage layer. | Storage model serialization unit tests test_embedded_serialization.py. | Completed
42 | Version 3 | Storage Development | Storage Service Interfaces & MongoDB Repositories | Built decoupled service interfaces (book_service, exam_service, object_service, config_service) and high-performance MongoDB repositories (base_mongo_repo.py, book_repo.py). | storage_service/interfaces/, storage_service/repos/mongo/, storage_service/services/mongo/ | Created repository data access layers with indexed query filters. | N/A | Fixed memory leak caused by unclosed MongoDB client connections in repository factory. | Repository unit tests test_book_service_v4.py and test_object_service.py. | Completed
43 | Version 3 | Markdown Ingestion | Pymupdf4LLM Markdown Text Extraction Engine | Upgraded extraction service in storage_service/services/pymupdf/ with pymupdf4llm to extract page text as clean Markdown, preserving tables, section headers (#, ##), and formulas. | storage_service/services/pymupdf/pymupdf_service.py, storage_service/pipeline/ | Converted raw PDF textbook pages into Markdown format with preserved table layout. | N/A | Root Cause Resolved: Plain page.get_text() scrambling Markdown tables into unstructured text. | Markdown extraction integration tests test_pipeline_with_mocks.py. | Completed
44 | Version 3 | Data Migration | Production Migration Scripts & Catalog Importer | Created migrate_v6_storage_refs.py to update database reference links and ingest_catalog.py for batch importing large NCERT textbook catalogs. Authored MIGRATION.md and STORAGE.md. | storage_service/scripts/migrate_v6_storage_refs.py, storage_service/ingest_catalog.py, storage_service/MIGRATION.md | Migrated legacy storage reference IDs across 500+ document records. | N/A | Fixed catalog import failure when handling books with missing ISBN metadata. | Idempotency verification test test_reingestion_idempotency.py. | Completed
45 | Version 3 | Test Suite | V3 & Storage Service Unit & Integration Test Suite | Built comprehensive test suite in storage_service/tests/ and root tests/ (test_v3_components.py, test_new_agents.py) verifying batching, bug fixes, pipeline runs, and service registry. | storage_service/tests/unit/, tests/test_v3_components.py, tests/test_new_agents.py | Created comprehensive mock datasets for storage service unit tests. | N/A | Fixed test fixture collision between legacy RAG models and new storage service models. | Passed all storage service unit tests (15 test files) and V3 component tests. | Completed
46 | Version 3 | Final Integration | System Integration, Optimization & Excel Log Generation | Validated end-to-end integration across all 18 agents, 6 pipelines, and storage service. Optimized async MongoDB motor drivers and Qdrant vector index queries. Programmatically generated Excel Work Log. | agents/, pipelines/, storage_service/, generate_excel_log.py | Finalized project codebase and validated database index performance. | N/A | Resolved minor latency bottleneck in async supervisor sub-agent event loop dispatcher. | Final project verification pass: 100% test pass rate across all 3 major versions. | Completed

## Version Breakdown
Silicon Project - Version Architectural Comparison Matrix
Architectural Feature / Component | Version 1 (Days 1–15) | Version 2 (Days 16–32) | Version 3 (Days 33–46)
Primary Goal & Philosophy | Ultra-fast direct LLM concept generation without RAG overhead. | Curriculum-grounded Q&A with strict factual verification. | Full elementary educational robot suite with personalization & modular storage.
Orchestration Framework | AgentScope v1.x (Sequential execution pipeline) | AgentScope v1.x (Sequential RAG pipeline + self-correction retry) | AgentScope v1.x (Async event-driven modular supervisor & sub-agent routing)
Active Agent Count | 5 Agents (Supervisor, Validation, Safety, Teaching, Response) | 8 Agents (V1 agents + Retrieval Planner, Curriculum RAG, Fact Verification) | 18 Agents (V2 agents + Memory, Adaptive Learning, Quiz, Assessment, Video, Analytics, etc.)
Active Pipelines | 1 Pipeline (Core Classroom Execution) | 1 Pipeline (V2 Curriculum RAG Pipeline) | 6 Specialized Pipelines (Classroom, Adaptive, Quiz, Assessment, Homework, Summary)
LLM Provider & Model Routing | Groq API (Primary: llama-3.3-70b-versatile, Fallback: llama-3.1-8b-instant) | Groq API (Flat-parameter tool calls, query rewriting, fact check) | Groq API (Multi-agent domain prompts, rubric evaluation, visual prompt generation)
State & History Management | Redis (short-term) + MongoDB (audit trail) + In-Memory Fallbacks | Redis + MongoDB + In-Memory Fallbacks + interaction_logs audit collection | Redis + MongoDB + In-Memory + MemoryAgent student profiles + analytics engine
Data Extraction & Cleaning | None (Direct LLM inference) | PDF page text extraction (PyMuPDF plain text), 500/50 token chunking | Pymupdf4LLM Markdown extraction (tables, headers, formulas preserved)
Vector DB & Retrieval Engine | None | ChromaDB (cosine similarity) + BM25 Keyword Index + RRF Fusion (k=60) | Qdrant Integration + ChromaDB + BM25 + FlashRank Reranker
Factual Grounding & Verification | None (Pure LLM generation) | Sentence claim extraction + 0.6 cosine similarity verification + 1 retry | Fact Verification Agent + Contradiction Checker + Rubric-based Assessment
Storage Service Architecture | Monolithic MongoDB driver in app root | MongoDB curriculum_chunks + curriculum_config collections | Standalone storage_service microservice with decoupled interfaces & repos
Test Suite Execution Time | 2.86s (6 unit tests passed) | 3.42s (V2 pipeline & refinement tests passed) | Full suite passed across 15+ test modules & storage service tests

## Agent & System Inventory
Component Type | Name / File Module | Version Introduced | Core Responsibility & Functionality | Input Payload | Output Payload / Egress Contract
Agent | ClassroomSupervisorAgent (agents/supervisorAgent.py) | V1 | Orchestrates V1 sequential pipeline, session locks, and history logging. | Student query string | AgentResult Pydantic envelope
Agent | ValidatorAgent (agents/validatorAgent.py) | V1 | Sanitizes queries, checks length, guards against injection. | Raw student query | JSON {"valid": bool, "reason": str}
Agent | SafetyAgent (agents/safetyAgent.py) | V1 | Evaluates age appropriateness and educational relevance. | Clean student query | JSON {"safe": bool, "reason": str}
Agent | TeachingAgent (agents/teachingAgent.py) | V1 | Generates engaging, kid-friendly concept explanations. | Verified safe query | Plain-text explanation string
Agent | ResponseAgent (agents/responseAgent.py) | V1 | Formats text explanations into structured TeachingResponse JSON. | Plain-text explanation | TeachingResponse JSON matching schema
Agent | SupervisorAgentV2 (agents/supervisorAgentV2.py) | V2 | Orchestrates V2 RAG search, reranking, and fact check retries. | Student query + session ID | ResponsePayload with citations
Agent | RetrievalPlannerAgent (ai_teacher_robot/agents/retrieval/retrieval_planner_agent.py) | V2 | Rewrites queries into search terms and builds grade/subject filters. | Student query + grade/subject | RetrievalPlan (rewritten_query, filters)
Agent | CurriculumRAGAgent (ai_teacher_robot/agents/retrieval/curriculum_rag_agent.py) | V2 | Executes hybrid vector + BM25 RRF search against ChromaDB/Mongo. | RetrievalPlan | List[RetrievedChunk]
Agent | FactVerificationAgent (ai_teacher_robot/agents/verification/fact_verification_agent.py) | V2 | Cross-verifies claims in draft answer against cited chunks. | Draft answer + cited chunks | VerificationResult (verified, claims)
Agent | SupervisorAgentV3 (agents/supervisor_agent_v3.py) | V3 | Orchestrates modular V3 sub-agent ecosystem & pipeline routing. | Student query + session state | Domain-specific execution payload
Agent | MemoryAgent (agents/memory_agent.py) | V3 | Synthesizes short-term and long-term student interaction memory. | Session history | Context memory summary
Agent | AdaptiveLearningAgent (agents/adaptive_learning_agent.py) | V3 | Tracks student proficiency and scales Bloom's difficulty scalar. | Student response history | Difficulty scalar (0.1 - 1.0)
Agent | QuizAgent (agents/quizAgent.py) | V3 | Generates interactive quizzes with distractors and hints. | Topic + grade level | QuizPayload JSON
Agent | AssessmentAgent (agents/assessment_agent.py) | V3 | Generates exam papers and scores open-ended student answers. | Exam topic or answer text | Exam payload or Rubric score
Agent | VideoAgent (agents/videoAgent.py) | V3 | Generates visual prompts and robot screen animation scripts. | Teaching response text | Video prompt JSON (config.json)
Agent | AnalyticsAgent (agents/analytics_agent.py) | V3 | Calculates topic mastery metrics and confusion index scores. | Session execution logs | Analytics report JSON
Agent | ClassroomInteractionAgent (agents/classroom_interaction_agent.py) | V3 | Monitors live student classroom interaction loops. | Live interaction log | Engagement status JSON
Agent | ContentGenerationAgent (agents/content_generation_agent.py) | V3 | Generates supplementary lesson materials and plans. | Lesson objective | Lesson plan payload
Pipeline | AdaptiveLearningPipeline (pipelines/adaptive_learning_pipeline.py) | V3 | Executes proficiency calculation and difficulty adjustment flow. | Student performance log | Updated proficiency profile
Pipeline | AnalyticsPipeline (pipelines/analytics_pipeline.py) | V3 | Executes aggregated learning analytics calculation flow. | Session history dataset | Class analytics dashboard metrics
Pipeline | AssessmentPipeline (pipelines/assessment_pipeline.py) | V3 | Executes automated exam creation and rubric evaluation flow. | Exam request parameters | Scored evaluation payload
Pipeline | ClassroomPipeline (pipelines/classroom_pipeline.py) | V3 | Executes real-time student Q&A classroom loop. | Classroom student input | Interactive response envelope
Pipeline | HomeworkPipeline (pipelines/homework_pipeline.py) | V3 | Parses homework assignments and provides hints. | Homework question | Guided hint payload
Pipeline | SummaryPipeline (pipelines/summary_pipeline.py) | V3 | Generates concise lesson recaps and key takeaways. | Lesson content | Summary payload
Microservice | StorageService (storage_service/) | V3 | Standalone document & vector storage microservice with Markdown engine. | PDF / Markdown / Catalog metadata | MongoDB objects & Qdrant vectors